## Ark1
AU Challenge 2019
Week 46: 13/11: Preparing
Time | Activity | Responsible | Comments
16:00-18:00 | Prepare The Lake Auditorium - put up everything in the foyer + check sound and tech | All | Put out ectention cords + plugs
16:00-17:00 | Jedrek makes a ressource map for Aarhus Municipality's case OBS: Should not be made public before the case is revealed. | Jedrek
17:00-17:45 | Fruit arrives from nemlig.com
| General audition, test sound and video, make sure all is in place, headsets charged, microphones charged | All | Welcome slides and company slides in place. Introduction videos to be placed on desktop.
| Prepare the three work locations to what extent possible, prepare where the consultants sit |  | Paper, post it (S and XL) and pens. Snacks, fruit and drinks. USB sticks in workplaces
| Make goodie bags |  | Place in auditorium
Test soap bubble machine, roll out carpet (we receive the carpet the 14)
Transport fruit + oat milk and goodies to the workplaces
Keyhanger
Make sign-up poster (across normal poster)
| Make 3 winner slides and 1 AU Challenge 2019 slide | Justyna
Week 46: 14/11: Case solving
Time | Activity | Responsible | Comments
7:30-9:00 | Meet and prepare the last things |  | - Jeppe Vontilius, lokale 310 (Aarhus Kommune) - Merete Barker, lokale 211 (VisitDenmark) - Eduard Biermann, lokale 204 (Hedeselskabet)
8:00 | Jedrek gets the presentations from the companies, make them into PDF and upload them to praticipant facebook | Jedrek | If companies have not arrived at 8.00, then make sure to do it when they arrive
9:00-9:30 | Welcome by AU Challenge representatives, formalities The three cases are represented by a company representative incl. | -AU Challenge formalities are presented by: - Nicoline (Aarhus Municipality) - Justyna (VisitDenmark) - Magnus (Hedeselskabet) | - Jeppe Vontilius, lokale 310 (Aarhus Kommune) - Merete Barker, lokale 211 (VisitDenmark) - Eduard Biermann, lokale 204 (Hedeselskabet)
9:20 | Put up the three cases on Facebook-page for participants | Jedrek
9:30-9:40 | The Team Coordinator shows the participants to their different locations | Nicoline: Aarhus Municipality Magnus: Hedeselskabet Justyna: VisitDenmark | - Hedeselskabet work in 1325-020, 1325-036 - VisitDenmark work in 1240-211 in the Bartholin building - Aarhus Kommune work in 1253 - 317 William Scharff
Rambøll consultants: Anders is at Hedeselskabet Erik is both at VisitDenmark and Aarhus Kommune Student consultants: Valdemar at Hedeselskabet Mads Studsgaard at AffaldVarme Mads Buhl at VisitDenmark
10:15 | Coffee and tea is delievered by Chemical Canteen | Team Coordinators | Canteen contact number:
11:00-13:00 | Prepare the sustainable marketplace - The Janitors not will help | Magnus and ??? | Stautrup fest udlejning contact number:
11-13 | Take-over as team coordinator for Magnus | Nanna
12:00 | Sandwiches are delivered to the three different workspaces | Team Coordinators | Canteen contact number:
12:45 | 1 person in each workroom cleans up after lunch | Team Coordinators
13:00-16:00 | Team Coordinators get a break | Merethe (replace Justyna) and Birgit (Replace Nicoline)
14:45 | Cake, coffee and tea is delievered by Chemical Canteen | Team Coordinators
17:00 | 2 people go to the canteen and start to prepare for dinner | Merethe and Nanna | Put out water and glasses, make buffet tables ready
17:40 | Dinner is delievered by Chemical Canteen | Merethe and Nanna | Canteen contact number:
17:55 | Team Coordinators escort the participants to the canteen | Team Coordinators
18:00-19:00 | Participants eat dinner in Samfundsfaglig Canteen
18:00-19:00 | A team member stays at each work location | Nanna, Merethe and Birgit
19:00 | 2-3 people clean-up in the canteen | Nanna, Merethe and Birgit
00:00 | Workspace closes
00:00-00:30 | Close up the different workspaces | Team Coordinators
Week 46: 15/11: Semi-final and finals
Time | Activity | Responsible | Comments
7:00-7:30 | Au Challenge team meet at the Lake Auditorium to prepare for the breakfast and the first day | All
7:30 | Breakfast is delivered | Merethe and Nanna
7:30-8:15 | Breakfast with participants
8:15-8:30 | Clean up after breakfast | Merethe, Nanna and Birgit
8:00-8:30 | Check of sound and tech in all auditoriums | Sabrina, Jedrek and janitors
8:30-12:05 | Semifinal in three tracks 8:30-8:35: Welcome by judge secretaries and introduction to the three judges. Say 9 + 5 introduce time signs 1 + 3 for presentation, but not time signs for questions 8:35-8:50: 1. Presentation (9 min presentation + 5 min Q&A) 8:50-9:05: 2. Presentation 9:05-9:20: 3. Presentation 9:20-9:35: 4. Presentation 9:35-9:50: Break 9:50-10:05: 5. Presentation 10:05-10:20: 6. Presentation 10:20-10:35: 7. Presentation 10:35-10:50: 8. Presentation 10:50-11:05: Break 11:05-11:20: 9. Presentation 11:20-11:35: 10. Presentation 11:35-11:50: 11. Presentation 11:50-12:05: 12. Presentation | Secretary for judges and timekeeper: Team Coordinators (Magnus, Justyna, Nicoline) | - Jeppe Vontilius, lokale 310 (Aarhus Kommune) - Merete Barker, lokale 211 (VisitDenmark) - Eduard Biermann, lokale 204 (Hedeselskabet) Things we need: 3 x signs with 3 min and 1 min.
12:05-12:45 | Lunch while judges deliberate | Team Coordinators bring lunch for judges | Judges remain in the auditorium while everyone else leaves. They should also have lunch served, we need chairs, so judges can sit around a table
12:45-13:15 | The judges give feedback to the presentations and announce the finalists
13:15-15:30 | The finalists work on implementing the feedback at their former work locations. Revised presentations is handed in no later than 15:30. | Team Coordinators take them back to their workspace
15:00 | Remember to put in Auditorium: Trophys under the table Judge sheets Signs 1 + 3 and bell for the end, Name cards for special seating THRP arrive 13.15 and put up instruments, rehearsal from 14.15 | Merethe and Jedrek
15:00-15:30 | Check of sound and tech in Per Kirkeby | Sabrina and Jedrek
14:30-15:30 | Companies and iniatives for the marketplace put up their stands | Magnus | Show the different companies where they should stand
15:30 | Hand in of presentations for final + teamname + Write a list on the door of the auditorium | Sabrina and Justyna | In front of Per Kirkeby
15:30 | Prepare table for judges in William Sharf Instruction for the five judges | Nanna and Jedrek Merethe | 5 chairs around table. Make sure they have something to drink and eat
16:00 | The grand final begins |  | Timekeeper for the final: Nanna Slide-master: Jedrek SoMe: Justyna/Sabrina
16:00-16:10 | Welcome by Brian Bech Nielsen, Rector
16:10-16:15 | VisitDenmark film is shown
16:15-16:30 | 1. Presentation
16:30-16:45 | 2. Presentation
16:45-17:00 | 3. Presentation
17:00-17:15 | Break with coffee, cake and possibility to visit the sustainable marketplace |  | Merethe and Magnus prepare coffee and cake | Justyna and Sabrina - Nicoline
17:15-17:20 | Aarhus Municipality film is shown
17:20-17:35 | 1. Presentation
17:35-17:50 | 2. Presentation
17:50-18:05 | 3. Presentation
18:05-18:20 | Break with coffee, cake and possibility to visit the sustainable marketplace |  | Merethe and Magnus prepare coffee and cake
18:20-18:25 | Hedeselskabets film is shown
18:25-18:40 | 1. Presentation
18:40-18:55 | 2. Presentation
18:55-19:10 | 3. Presentation
19:10-19:40 | Break with snacks and music while the judges deliberate |  | Merethe and Magnus prepare break with snacks Put chips in brown paper bags 25 + 25 Deliberation in William Scharff Nanna and Jedrek show the judges to the room and make sure they have water and snacks | Get glasses ready, put chips in bags, incets
19:10 | Put the thropies up on the table
19:40-20:00 | Announcement of winners + show winner slides | Company representatives | Trees are handed aut by our team + Birgit
20:00 | Start the bubble machine when all thre winning teams are on stage together | Magnus | Ask THRP to play
20:00 | Get statements from the three winner teams as well as Carsten, Hanne and Victoria | Merethe and Maciej Marina | Remember camera tech
20:00-20:30 | Bubbles, chips and insect snacks | All
20:30- | Clean up | All
Contact information on Team
Title | Name | Number | Comment
Project Manager
Head Coordinator
Team Coordinator 1 |  |  | Has a key for the workroom
Team Coordinator 2 |  |  | Has a key for the workroom
Team Coordinator 3 |  |  | Has a key for the workroom
Team
Team
Team
Building staff, Lake auditorium
Building staff, North/eastern corner
Building staff, Bartholin building
Chemical canteen
Photographer AU |  |  | Torsdag: 9-10 and 13-14
Freelance Photographer |  |  | Fredag: 18:00-20
Video