# Sample process plan – template

This template is an example of how to approach planning strategy work. It’s intended for inspiration, and it can be tailored to your needs in terms of timing, involvement and scope. Sometimes it may be necessary to adjust a plan along the way because some steps turn out to take more time, to build consensus or involve everyone whose input you’d like to have to ensure their buy-in.

You’re encouraged to use the template as a framework that can be adapted before use and as needed subsequently.

| OVERVIEW | SUGGESTED ACTIVITY | TIMING | OWN TIMING - NOTE below: |
| --- | --- | --- | --- |
| Before you begin: clarify your scope and objectives | Determine the scope of the project (unit/theme) – see secondary questions on slide 4 | Before you arrive at your shared situation awareness. |  |
| Develop shared situation awareness. | Meeting/workshop based on process suggested on slide 7 | 1-2 hr. meeting |  |
| Craft strategic intent statement | Manager or small working group crafts proposals for strategic intent statements Or the strategic intent is developed on the background of the working question on slide 10 | 2-4 weeks after development of shared situation awareness |  |
| Involve more people in crafting strategic intent statement | Test strategic intent statement Present the strategic intent for fellow managers, staff, leadership team not involved in its development and get their input. Adjust strategic intent statement based on input from above. | 1-3 weeks after completion of first draft of strategic intent statement |  |
| Stakeholder analysis (where relevant) | Manager or small working group carries out stakeholder analysis to get an overview of who will be affected and what stakeholders need to be activated. See slide 19 | Before articulating unifying movements |  |
| Articulate unifying movements | Develop proposals for unifying movements statements based on the description on slide 12, in a working group. Or the manager/a smaller working group develops proposals and then tests/discusses whether they resonate with relevant stakeholders, adjusting the wording based on input. | Shortly after the strategic intent has been formulated – possibly in connection with the finalisation of the strategic intent. |  |
| Involve more staff in the formulation of the unifying movements | Test the unifying movements Present them to fellow managers, staff, leadership team not involved in its development and get their input. | Before making short-term to-do lists |  |
| Make short-term to-do lists | For each unifying movement, the person(s) with the greatest influence on and responsibility for the unifying movement should make a short-term to-do list (see slide 14 for tips). This could be the manager, other members of management, selected staff members or working groups. | 1-3 weeks after adoption of unifying movements |  |
| Work with the strategy in the day-to-day | After the short-term to-do lists have been made, the items on the list should be done, prioritised in the day-to-day and revised if necessary. | Regularly |  |
| Regular follow-up | Decide on a cadence for follow-up on strategic work in the day-to-day It’s a good idea to revisit this every six months so it can be adjusted to reflect any changes, for example in conditions or tasks, that might lead you to revise the unifying movements or to-do lists. Can be done more often if the to-do lists cover shorter time periods. ​See slide 16 for suggestions. | 2 hrs. every six months (for example) |  |